## Completion Percentage
C3 Label Application
List of Activities | Days Needed | Completed | Remarks
1. Meeting with the Client
A. Data Gathering | 3 | TRUE |  | 3
2. Creation of documents
A. Creation of Process flow diagram, flowchart, use case diagram, etc. | 7 | TRUE |  | 7
B. Checking of documentation with the client including approval and revision. | 1 | TRUE |  | 1
C. Documentation client approval for correctness and validation. | 2 | TRUE |  | 2
D. Adjust the documentation base on user comment and suggestions. Present the revised documentation. | 2 | TRUE |  | 2
3. System User Interface Design (UI)
A. Create a user interface for the C3 Label. | 2 | TRUE |  | 2
B. Cheking of UI with the client including approval for correctness and validation. | 0 | TRUE |  | 0
C. Adjust the UI base on user comment and suggestions. Present the revised documentation. | 2 | TRUE |  | 2
4. System Coding
A. Create the C3 Labeller Format 1 - 5 (Back-End) | 6 | TRUE |  | 6
B. Present the C3 Labeller to the requestor | 1 | TRUE | Waiting for Japanese Approval, CO Sir Jojo | 1
C. Adjust the coding base on user comment and suggestions. Present the revised documentation. | 2 | TRUE |  | 2
5. User Testing and Acceptance
A. System Testing | 5 | TRUE |  | 5
B. Migration and Roll-out | 1 | TRUE |  | 1
Completed Days | 34
Total Number of Days | 34 |  |  | 34
Completion Percentage | 100%

## Detailed Gantt Chart
C3 Label Application
List of Activities | Month | May | [15 empty] | June
| Days | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
1. Meeting with the Client
A. Data Gathering | Target | bar: May 16 to May 18
Actual | bar: May 18
2. Creation of documents
A. Creation of Process flow diagram, flowchart, use case diagram, etc. | Target | bar: May 19 to May 20; May 23 to May 27
Actual | bar: May 25 to May 27
B. Checking of documentation with the client including approval and revision. | Target | bar: May 30
Actual | bar: May 30
C. Documentation client approval for correctness and validation. | Target | bar: May 31 to June 1
Actual | bar: May 30
D. Adjust the documentation base on user comment and suggestions. Present the revised documentation. | Target | bar: June 2 to June 3
Actual | bar: May 30
3. System User Interface Design (UI)
A. Create a user interface for the C3 Label. | Target | bar: June 6 to June 7
Actual | bar: May 30
B. Cheking of UI with the client including approval for correctness and validation. | Target | bar: June 7
Actual | bar: June 3
C. Adjust the UI base on user comment and suggestions. Present the revised documentation. | Target | bar: June 8 to June 9
Actual | bar: June 3
4. System Coding
A. Create the C3 Labeller Format 1 - 5 Back-end | Target | bar: June 10; June 13 to June 17
Actual | bar: June 6 to June 10; June 13 to June 17
B. Present the C3 Labeller to the requestor | Target | bar: June 20
Actual | bar: June 6
C. Adjust the coding base on user comment and suggestions. Present the revised documentation. | Target | bar: June 21 to June 22
Actual
5. User Testing and Acceptance
A. System Testing | Target | bar: June 23 to June 24; June 27 to June 29
Actual
B. Migration and Roll-out | Target | bar: June 30
Actual

## Sheet3
Legend
Target
Actual
Recovery
On-going